## Hoja1
Project: | THE DIFFERENCE ENGINE |  | REF:
missing
Page | Status | Notas | comienzo
header | done |  | en desarrollo | * Sujetas a modificaciones de mejora
footer | done |  | Maquetada
/index.html | a la espera del cliente
/templates/about.html | done |  |  | marckup task : #26360145
/templates/team.html | done
/templates/team-members.html | done | empty
/templates/research.html | done
/templates/projects.html | done
/templates/projects/womens-power.html | done
/projects/womens-power-index/about-us | done
/projects/womens-power-index/criteria-methodology.html | missing
/projects/womens-power-index/research.html | missing
/projects/womens-power-index/research#nav-state-of-the-index | missing
/templates/projects/supercharger.html | done
/templates/projects/supercharger/who-should-apply.html | done
/templates/projects/supercharger/why-supercharger.html | done
/templates/news-and-events.html | done
/templates/news-and-events-single.html | done | single
/templates/partners.html | done
PENDIENTES
Unificar el main
verificar las url's
optimizar css modular hero + bloques de contenido
hacer buttons en womens-power - video
text format optimizar
image container optimizar
grillas aparte
png a jpg y tamaños